## Governance Packet Chain
Twelve Pillar Protocol — Provisional CRP Governance Packet Chain
Packet Name | File | Status | Depends On | Next Action | Completed By
CRP Bootstrap Status Packet | CRP_Bootstrap_Status_Packet.md | COMPLETE | — | Review findings | Founding steward
OQ-CRP-1 Interpretation Ruling (draft) | OQ_CRP_1_Provisional_CRP_Interpretation_Ruling.md | COMPLETE (background record) | CRP Bootstrap | Retained as background; no action needed | —
OQ-CRP-1 Adopted Interpretation | OQ_CRP_1_Adopted_Interpretation.md | ADOPTED — signatures pending | OQ-CRP-1 Ruling | Founding steward signs and dates | Founding steward
Provisional CRP Constitution Packet | Provisional_CRP_Constitution_Packet.md | TEMPLATE — not executed | Adopted Interpretation signed | Execute steps in order after input form complete | Founding steward
Provisional CRP Owner Decision Record | Provisional_CRP_Owner_Decision_Record.md | DECISIONS RECORDED — signatures pending | Constitution Packet | Founding steward signs and dates | Founding steward
Provisional CRP Human Input Form | Provisional_CRP_Human_Input_Form.md | NOT STARTED | Owner Decision Record signed | Complete all fields with real data (eligibility pool, observers, seed, draw method, sponsor list, reasons, minority views) | Founding steward
Provisional CRP Draw and Roster Certification Packet | Provisional_CRP_Draw_and_Roster_Certification_Packet.md | TEMPLATE — not executed | Human Input Form COMPLETE | Execute Steps 1–6 in sequence; do not skip ANNEX_U2 gate | Founding steward
Federated Ombuds Constitution Packet | Federated_Ombuds_Constitution_Packet.md | TEMPLATE — not executed | Provisional CRP certified | Proceed after roster certification COMPLETE | Founding steward
Sub-Ombuds Confirmation Packet (5 seats) | Not yet created | NOT CREATED | Provisional CRP operative | Issue implementation contract to Claude | Claude
Category C Corpus Fixes (P2-B through P2-G) | See remaining-blockers-agent-plan.md | NOT STARTED | None (not launch blockers) | Batch implementation contract when ready | Claude

## Open Questions
Open Questions — Provisional CRP Bootstrap Chain
Question ID | Question | Source | Status | Notes
OQ-CRP-1 | Does provisional CRP satisfy ANNEX_AI Section 2.1 CRP role for sub-Ombuds confirmation? | OQ_CRP_1_Adopted_Interpretation.md | RESOLVED — Option A adopted | Provisional CRP may confirm sub-Ombuds for bootstrap period only; source tension acknowledged
OQ-PCRP-1 | Who administers the mixed-lot draw? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | Founding steward, subject to observer attestation; may not resolve challenges alone
OQ-PCRP-2 | How many members does the provisional CRP have? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | 5 seats
OQ-PCRP-3 | What are the eligibility pools? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | Verified founding participants + qualified external reviewers; full exclusion list per ANNEX_U Section U2 + OQ-PCRP-3 conflict list
OQ-PCRP-4 | How is randomness produced and audited? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | Public seed + reproducible method; seed, method, input pool, output all published before draw
OQ-PCRP-5 | How long is the challenge window? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | 14 days from draw result publication
OQ-PCRP-6 | Who receives and resolves challenges? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | Received by founding steward; resolved by observer panel; founding steward may not override
OQ-PCRP-7 | Observer panel qualifications and minimum size? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | Minimum 3 members; external to founding steward, candidate pool, sub-Ombuds pool, reviewed vendors/actors
OQ-PCRP-8 | Replacement draw if challenge sustained? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | Single-seat replacement draw using same method, new seed, same observers and 14-day window
OQ-PCRP-9 | Where are artifacts published pre-Article VII dashboard? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | docs/governance/ with pattern Provisional_CRP_[ArtifactType]_[YYYY-MM-DD].md; mirror to Article VII dashboard when operational
OQ-PCRP-10 | Quorum threshold for sub-Ombuds confirmation? | Provisional_CRP_Owner_Decision_Record.md | DECIDED | 4-of-5 if all seated; minimum 4 seated before any vote; 2/3 of seated count rounded up

## ANNEX_U2 Effectiveness Gate
ANNEX_U2 Effectiveness Gate — All conditions must be COMPLETE before any provisional CRP action takes effect
Condition | Source | Status | Artifact Required | Notes
Challenge window closed (14 days from draw result publication) | ANNEX_U Section U2; OQ-PCRP-5 | NOT MET | Challenge closure artifact | Window opens on draw result publication date; closing date = open date + 14 days
All challenge responses published | ANNEX_U Section U2 | NOT MET | Challenge log with written responses per challenge | Observer panel resolves; founding steward routes only
Observer panel attestation published | ANNEX_U Section U2 | NOT MET | Provisional_CRP_ObserverAttestation_[date].md | Minimum 3 observers must sign; attestation scope limited to process rules
Sponsor list published | ANNEX_U Section U2 | NOT MET | Provisional_CRP_SponsorList_[date].md | Must publish BEFORE any provisional ruling takes effect
Conflict disclosures per member published | ANNEX_U Section U2 | NOT MET | Per-member conflict disclosure files | Must publish BEFORE any provisional ruling takes effect
Written reasons for provisional CRP constitution published | ANNEX_U Section U2; ANNEX_N N3 | NOT MET | Provisional_CRP_WrittenReasons_[date].md | Must publish BEFORE any provisional ruling takes effect
Minority views published (or 'none filed' declaration) | ANNEX_U Section U2 | NOT MET | Provisional_CRP_MinorityViews_[date].md | Must publish BEFORE any provisional ruling takes effect
Challenge path notice published | ANNEX_U Section U2 | NOT MET | Provisional_CRP_ChallengeNotice_[date].md | Must publish BEFORE draw result; included in challenge window notice
Sunset date declared and published | ANNEX_U Section U2; ANNEX_N N2 line 28 | NOT MET | Sunset date in Owner Decision Record + roster certification | 8 quarters from certification date (~2 years); all provisional actions auto-expire
Roster/quorum certification published and COMPLETE | Follows from all conditions above | NOT MET | Provisional_CRP_RosterCertification_[date].md | Final gate; ALL conditions above must be COMPLETE first; this is the operative date

## Category A Human Actions
Category A — Human Governance Actions Required (dependency order)
# | Action | Source | Dependency | Status | Notes
1 | Sign OQ-CRP-1 Adopted Interpretation | OQ_CRP_1_Adopted_Interpretation.md | None | PENDING SIGNATURE | Founding steward must date and sign; no appointments have occurred
2 | Sign Provisional CRP Owner Decision Record | Provisional_CRP_Owner_Decision_Record.md | OQ-CRP-1 signed | PENDING SIGNATURE | Records process parameters only; no draw has occurred
3 | Complete Human Input Form with real data | Provisional_CRP_Human_Input_Form.md | Owner Decision Record signed | NOT STARTED | Real eligibility pool, observer panel (3+), seed source, draw method, sponsor list, written reasons, minority views
4 | Identify and appoint external observer panel (3+ members) | OQ-PCRP-7 | Human Input Form section complete | NOT STARTED | Must be external to founding steward, candidate pool, sub-Ombuds pool, reviewed vendors; publish appointment record before draw
5 | Publish eligibility pool and exclusion screening records | ANNEX_U Section U2; OQ-PCRP-3 | Observer panel appointed and published | NOT STARTED | Must publish before draw; use template in Step 1 of draw packet
6 | Publish pre-draw ANNEX_U2 artifacts (sponsor list, written reasons, minority views, challenge path, sunset date) | ANNEX_U Section U2 | Eligibility pool published | NOT STARTED | All five must be COMPLETE before draw runs; use templates in draw packet
7 | Conduct mixed-lot draw | ANNEX_N N2; OQ-PCRP-1 | Steps 5 and 6 complete; seed and method published; observers present | NOT STARTED | Founding steward administers; observers present or contemporaneously notified; use Step 3-4 of draw packet
8 | Publish draw result; open 14-day challenge window | Draw packet Step 4 | Draw conducted | NOT STARTED | Challenge window starts on publication date; publish challenge notice (Step 5 of draw packet)
9 | Receive challenges; route to observer panel for resolution | OQ-PCRP-6 | Challenge window open | NOT STARTED | Founding steward receives; observer panel publishes written resolution per challenge; conduct replacement draw if needed (OQ-PCRP-8)
10 | Close challenge window; publish closure artifact | OQ-PCRP-5 | 14 days elapsed; all challenges resolved | NOT STARTED | Challenge closure artifact confirms no unresolved challenge remains
11 | Obtain and publish observer attestation | ANNEX_U Section U2 | Challenge window closed | NOT STARTED | 3+ observers sign; use attestation template in draw packet Step 6a
12 | Issue provisional CRP roster/quorum certification | Draw packet Step 6 | All ANNEX_U2 gate conditions COMPLETE | NOT STARTED | Operative date of provisional CRP; minimum 4 of 5 seats must be filled for sub-Ombuds confirmation to proceed
13 | Proceed to sub-Ombuds confirmation (5 seats) | Federated_Ombuds_Constitution_Packet.md | Provisional CRP certified | NOT STARTED | One 4-of-5 confirmation vote per seat; 60-day public challenge period per seat per ANNEX_AI Section 2.1
14 | Run FC-YT1/FC-YT2 Ombuds review | INVARIANTS.md INV-LAUNCH-1 | At least 4 of 5 sub-Ombuds seated | NOT STARTED | Clears INV-LAUNCH-1 gate condition; unblocks real-persons enrollment
15 | Formally assign Tier 0 token mechanism (TSP) | AZ2.1 pre-launch gate; remaining-blockers-agent-plan.md | Independent of Ombuds chain | NOT STARTED | Technical decision by founding steward; not dependent on CRP or Ombuds